## Slide 1: Lead and Lag
Lead – amount of time that precedes the start of work on another activity
Lag – amount of time after one activity is started or finished before the next activity can be started or finished
Notes: <number>

## Slide 2: Other network diagrams
PERT – Performance Evaluation and Review Technique
  Better for software-oriented projects
  Uses 3 time estimates to determine most probable
CPM – Critical Path Method
  Better for construction type projects
  One time estimate
Notes: <number>

## Slide 3: Activity
Create a network diagram from the WBS for the case study
Notes: <number>

## Slide 4: Scheduling
Establish scheduling assumptions
Estimate the resources, effort and duration
  Effort – time that it takes to work on the activity
  Duration – the time to complete the activity
Determine calendar dates for activities
Adjust individual resource assignments
Chart final schedule
Notes: <number>

## Slide 5: Estimating Time
Have people who are doing the work provide the estimates
Get an expert’s estimate
Find a similar task
Look for relationship between activity and time (parametric estimate)
Educated guess
Notes: <number>

## Slide 6: PERT Estimating
Optimistic estimate (OD)
Most likely (MLD)
Pessimistic estimate (PD)
Expected = [OD + 4(MLD) +PD] / 6
Notes: <number>

## Slide 7: Contingency
Don’t pad estimates
  Will never get good estimates
  Adds expense and time
Add contingency as an activity
  Typically 10-15%
Notes: <number>

## Slide 8: Critical Path & Float
Critical Path
  Sequence of tasks that forms the longest duration of the project
Float
  Amount of time that an activity may be delayed from its earliest possible start date without delaying the project finish date
  Latest possible finish date – earliest possible start – duration = total float
Notes: <number>

## Slide 9: Normalizing the Schedule
Assign people to the schedule
Start with the critical path first, non-critical tasks second
Notes: <number>

## Slide 10: Loading and Leveling
Resource Load – the amount of work that is assigned to a resource
Resource Leveling – redistribution to even out the distribution of work across all resources
Notes: <number>

## Slide 11: Scheduling Tips
Ensure that learning time is identified
Ensure that administration time is included
Be aware that resources seldom work 100% of the time on one project
Notes: <number>

## Slide 12: Activity
Create a schedule for the case study
Notes: <number>

## Slide 13: Budgeting
Budget = People + Resources + Time
Notes: <number>

## Slide 14: Budgeting Levels
Ballpark Estimate
Rough Order of Magnitude
Detailed Estimate
Notes: <number>

## Slide 15: Direct & Indirect Costs
Direct costs
  Directly attributed to the project
Indirect costs
  Shared amongst other projects
Notes: <number>

## Slide 16: Types of Budgeting
Bottom-up
Top-Down
Phased
Notes: <number>

## Slide 17: Contingency Reserve
10-15% of budget is normal
Don’t pad but manage the contingency
Notes: <number>

## Slide 18: Activity
Build a budget for the case study
Notes: <number>