## Slide 1
<number>
University of Diyala
College of Engineering
Project Management
Third Stage
Dep. of Civil Eng.
Lecturer
M.S. Sultan N. Al-Gaisi
2017-2018
Notes: <number>

## Slide 2
<number>
PDM Network Development
Activity ID Description Duration Successor Timelags
Mobilization 5 15
Excavation 10 20 SS 5
FF 5
20 Foundations 10 -
10
Mobil
5
15
Excav
10
20
Foundations
10
FF 5
SS 5

## Slide 3
<number>
PDM Network Rules
All activities must be connected
No open ends or dangling activities are allowed
Activity ID numbers should be unique (numbers should not be duplicated)
Logic loops are not allowed

## Slide 4
<number>
Terms of Interest
Predecessor
Successor
Dependency
Network Logic
Dangling Activities
Finish to Finish
Sequential
Start to Start
Overlapping
Time Lags
Finish to Finish

## Slide 5
<number>

## Slide 6
<number>

## Slide 7
<number>

## Slide 8
<number>

## Slide 9
<number>
PDM Home Work Assignments
# 5 & #6

## Slide 10
<number>

## Slide 11
<number>
Home work Assignment #6: Concrete Foundation Project
Develop a PDM diagram for the following activity data and determine the project duration in days. Identify the critical path and show ES, EF, LS, LF, and TF on the diagram.

## Slide 12
<number>
Activity Id | Description | Duration | Successor | Time Lag
10 | Notice To Proceed | 1 | 20 30 75 | 
20 | Excavation | 10 | 25 25 | SS8 FF0
25 | Install Formwork | 5 | 70 | 
30 | Prepare Rebar Shop Dwgs | 10 | 40 | 
40 | Rebar Shop Dwgs Rvw & Aprvl | 5 | 60 60 | SS3 FF0
60 | Rebar Fabrication & Delivery | 10 | 70 | 
70 | Install Rebar | 5 | 100 | 
75 | Submit Mix Design | 10 | 80 | 
80 | Approve Mix Design | 5 | 100 | 
100 | Place Concrete | 1 | 110 | FS28
110 | Ready for Steel Erection | 1 |  | 

## Slide 13
<number>
Schedule Compression
Examine the critical path
Select activities that can be compressed
Select activities that can be overlapped
Perform work on week ends and/or add additional shifts
Change construction method, e.g. precast instead of cast-in-place

## Slide 14
<number>

## Slide 15
<number>

## Slide 16
<number>

## Slide 17
<number>

## Slide 18
<number>
Estimating Activity Durations
Time Units: Years (Mega projects)
: Months (Conceptual estimate)
: Weeks (Conceptual estimate)
: Days Most projects
: Hours Used in process work

## Slide 19
<number>
Productivity Depends On:
  Nature of work
  (repetitive tasks increase productivity)
  Labor productivity
  (training and skills increase productivity)
  Seasonal conditions
  (weather: reduced productivity)
  Work restrictions
    (shutdown periods, security issues)
  Quality of work
  (tight tolerances: reduced productivity)
  Concurrent activities
  (too many people working at the same time: reduced productivity)

## Slide 20
<number>
Source
  Quantity take-off/MEANS Estimating Books
  Bid estimates
  Past experience
  Outside info
  Industry & trade organization
  Subcontractors/manufacturers/fabricators/
  vendors